CARE Uganda

ToRs – PS Business Development Consultant (Kampala-based, three months extendable by three + full-time)

#### Why this role:

CARE Uganda holds assets the private sector needs: organised VSLAs at scale, trusted community access, group records and data, a facilitator network, and enterprise and market-linkage capability. What we have not done is systematically test who will pay for them, and for what.

We have done the thinking. This role does the pitching. Not a strategy assignment, not Facility design, not internal proposition-refinement. Market-facing from week one, with a signed deal as the headline objective.

#### Scope:

Into the market weekly - banks, fintechs, agribusinesses, funds - and deliberately beyond financial inclusion: recycling, clean cooking and sustainability-bond holders, digital payments, FMCG distribution, workforce development (BDS). Open with the counterparty's problem, test a CARE offer against it, establish willingness to pay, move live conversations to proposal and agreement.

Convert the warm/new pipeline - seven potential opportunities are already on the table. The consultant inherits these, not a blank sheet + adds their own exposure and what CARE shall continue to bring to the table

Build the sellable offer - turn what the market actually asks for into costed, repeatable CARE service lines with unit prices; avoid what we always want to table i.e., capability statements, etc

Transact, don't architect - start from the deal; propose a vehicle only where a specific transaction requires one.

#### Deliverables and success:

| By end of | Tangible outcome |
| --- | --- |
| Day 30 | - First agreement signed or term sheet. Live pipeline of named counterparties with problem, offer tested, stage. 20+ conversations held. |
| Month 2 | - 3 written, costed propositions with decision makers. Ensibuuko commercial model formally tabled. Priced CARE service lines drafted. |
| Month 3 | - At least one signed fee-for-service agreement or commercial commitment, with two more in active negotiation. Substantive conversations with decision makers, qualified opportunities and costed propositions in motion also count as evidence of progress. +15 conversations logged and a documented read on where willingness to pay does and does not exist. |

Negative findings count. We are a ‘learning-mindset’ entity at CARE Uganda; honest conversations that close a door better than another quarter of internal refinement. Extension is conditional on the month-3 outcomes.

#### Profile:

Essential: commercial background in banking, fintech, agribusiness, investment or corporate BD. Commercial B2B origination and closing experience is essential - demonstrable record of personally opening doors, shaping propositions, negotiating and closing business in Uganda. Existing, usable network at C-suite and board level in Kampala. Able to read a counterparty's P&L and build a proposition around it. Comfortable being told no, repeatedly, and moving the same day.

Desirable: background in any commercial sector - banking, fintech, agribusiness, telecoms, FMCG, technology, energy, professional services. Sector is secondary to Uganda market knowledge, a usable senior network, an understanding of how companies make money, and the ability to turn a counterparty’s commercial problem into something CARE can sell.

Candidate assessment: shortlisted candidates will be asked to walk through three deals they personally originated or closed - covering how they reached the decision maker, the problem they identified, what they proposed, approximate value, and specifically what they did to get it over the line.

#### Reporting:

Reports to the Country Director. Works day-to-day with the EIFF unit and PSE team. Technical accompaniment from the Associate VP for Economic Growth and PSE. Fortnightly pipeline review against the deliverables section.